**STAR - Provisional agenda for M8-16**

Outline of tasks to be carried out in WP3:

* Development of Training Material for use by DPAs
  + Development of training scenarios
    - DPA personnel,
    - DPOs,
    - judges and other lawyers,
    - civil servants,
    - private sector.
  + Development of the Training Materials for the training of DPA personnel
  + Development of the Training Materials for the training of DPOs
  + Development of the Training Materials for the training of judges and lawyers
  + Development of the Training Materials for the training of civil servants and public sector employees
  + Development of the Training Materials for the training of the private sector
* Development of training material for use by DPOs
  + Development of training scenarios
  + Development of the Training Materials to be used in the public sector
  + Development of the Training Materials to be used in the private sector

Proposed timeline:

* Mid-september: preparation of general materials (slides and list of handouts) for the 11 topics described in D2.4 (VUB, revision: TRI/NAIH)
* Mid-/end of september: list of corresponding national data protection acts and sector-specific laws (examples for public sector in the GA: ministries of justice or home affairs; for the private sector: telecom and financial industry) (???)
* Mid-/end of october: development of training scenarios
  + plan/structure of the lecture,
  + objectives,
  + key issues,
  + ideas for discussion,
  + use-cases,
  + examples,
  + group tasks,
  + differences between training experts and non-experts,
  + etc. (???)
* November-february: refining

the general materials and topics are more or less set, the goal would be to have different template use-cases/examples and tasks for each group of audience (or the same example but from a different stakeholder’s point of view) as well as a catalogue of applicable laws.