Kick-off meeting

1. Opening remarks and the adoption of the agenda
2. Discussion on the conduct of the STAR II project (2018-2020):
    1. Overview of the aims, structure and timeline of the project
    2. Discussion on the project management and budget
      1. discussion of the allowance distribution method
    3. Clarifications as to the activities to be undertaken
      1. the set-up of the Advisory Board
      2. interviews with the DPA-s and contacting SME-s (DPA’s awareness raising efforts and SME’s experience with the GDPR)
      3. the identification of the needs of the SME-s
      4. establishment of the radio campaign
      5. the operation of the hotline (technical details and timing; trial hotline)
      6. statistical analysis of the questions raised be the SME-s
      7. drafting the handbook and the guidance
    4. Discussion on the organization and participation in the events related to the project:
      1. organization of three validation workshops
      2. the final conference (Budapest)
    5. Discussion on the dissemination strategy:
      1. logo
      2. project’s website
      3. project’s social media accounts
      4. press releases
      5. peer-reviewed articles and other publications
      6. bi-monthly newsletter
    6. Clarifications as to the role of each partner in each activity
    7. Responsible Contributions to deliverables
3. Adoption of:
    1. Rules for the internal review of work
    2. Deliverable templates
    3. Standard terminology used in deliverables
    4. Standards of internal and external communication
      1. periodic coordination meetings and/or monthly conference calls
    5. Standards for “pooling” contacts and knowledge
    6. Standard reference system
4. A.O.B.