Kick-off meeting

1. Opening remarks and the adoption of the agenda
2. Discussion on the conduct of the STAR II project (2018-2020):
    1. Overview of the aims, structure and timeline of the project
    2. Discussion on the project management and budget
      1. discussion of the allowance distribution method
        1. we suggest the WP based distribution method (5 times during the project, in proportion of 10%-20%-40%-20%-10%)
      2. discussion of the technical details of the reporting (the method of preparing and sending the required documents)
        1. preparing the timesheets in a monthly breakdown
        2. sending the timesheets, payslips, invoices, attendance lists, etc. to the Coordinator at the end of the WP-s
    3. Clarifications as to the activities to be undertaken
      1. the set-up of the Advisory Board suggestions of the possible members)
      2. interviews with the DPAs and contacting SMEs (DPA’s awareness raising efforts and SME’s experience with the GDPR)
        1. tasks to be undertaken in detail
      3. the identification of the needs of the SMEs
        1. methods to identify and reach SMEs
      4. establishment of the radio campaign
        1. discussion of the texts and scenarios of the radio spot
      5. the operation of the hotline
        1. languages of the hotline, contact to the persons who will help in other languages
        2. preparing a guide for the colleagues of the hotline (extract of the handbook ?)
      6. statistical analysis of the questions raised be the SMEs
      7. drafting and translation of the handbook and the guidance
        1. planned length of the handbook and the guidance
    4. Discussion on the organization and participation in the events related to the project:
      1. organization of three validation workshops
        1. finalization of the location of the workshops
      2. the final conference (Budapest)
    5. Discussion on the dissemination strategy:
      1. decision on the logo
      2. project’s website
      3. project’s social media accounts
      4. press releases
      5. peer-reviewed articles and other publications
      6. bi-monthly newsletter
    6. Clarifications as to the role of each partner in each activity
    7. Confirming the responsible contributions to deliverables
3. Adoption of:
    1. Rules for the internal review of work
    2. Deliverable templates
    3. Standard terminology used in deliverables
    4. Standards of internal and external communication
      1. periodic coordination meetings and/or monthly conference calls
    5. Standards for “pooling” contacts and knowledge
    6. Standard reference system
    7. Signature of the Consortium Agreement
4. A.O.B.